# Consultation Traceability and Validation Record

Regional Local Youth Agri-Procurement Strategy | Six sessions, 11 August–15 September 2026

# Purpose and scope

This record shows how 90 recommendation entries from all six Committee session reports informed the revision of CAYAB Recognition and Procurement Strategy dated 16 September 2026. It connects the original recommendation and status to numbered strategy clauses, explains what changed and keeps unresolved decisions visible. The revised strategy preserves the baseline request for recognition of CAYAB’s institutional strengthening and its strategic contribution; it does not seek mandatory national implementation.

The 90 entries are 10 Session 1 proposals plus the 12, 15, 22, 18 and 13 entries in Sessions 2–6. Repeated themes are retained to preserve provenance. This is a new reconciliation of the six Committee registers, not a claim that the earlier 29-entry working register has 90 unique recommendations. Narrative questions and the final synthesis inform the drafting explanations and open issues. Keynote material is not treated as a separate vote or institutional commitment.

# How to read the record

Source status is the historical classification in the session report. Drafting response means the proposal has been incorporated, expanded or referred in this revision; it is not a change to the source status. Clause numbers refer to the revised Strategy. C01–C18 identify change packages. A clause supported by one session may still contain a technical question left open in another.

| Session | Entries | Recorded status summary |
| --- | --- | --- |
| 1 | 10 | 10 Proposed for LoA Committee consideration |
| 2 | 12 | 6 Supported; 2 Mixed View; 2 Referred; 1 Unresolved; 1 No formal determination recorded |
| 3 | 15 | 11 Supported; 3 Referred; 1 Mixed View |
| 4 | 22 | 21 Supported; 1 Referred |
| 5 | 18 | 15 Supported; 2 Unresolved; 1 Referred |
| 6 | 13 | 7 Supported in discussion; 5 Further technical review; 1 Referred |

Session 6 recommendation statuses are recorded. Its report separately states that formal counts and dispositions for five validation propositions are not included. The package therefore presents a consultation-informed revision with recorded validation outcomes, not a certification that every revised clause has received formal approval.

# What changed in the strategy

## C01 | 1.6 Consultation basis and validation status

Baseline: The baseline acknowledges consultation without identifying the six-session record or limits of validation.

Revision: This revision incorporates the Regional Consultation and Validation Series held from 11 August to 15 September 2026 and its final consolidated report. The historical consultations considered the proposed Local Agriculture First Policy (LAFP); applying those findings to this Strategy is a subsequent drafting step. See revised clause for the complete provision.

Evidence links: S1-R02, S6-R13.

## C02 | 6.2.1 Demand planning and buyer readiness

Baseline: Procurement planning is encouraged, but the information and operational conditions needed by buyers and suppliers are unspecified.

Revision: For an agreed activity, buyers and responsible technical partners should document products, quantities, seasonal demand, specifications, food-safety requirements, delivery locations and frequency, acceptable delivered cost, receiving capacity and payment arrangements before suppliers commit production. Buyer forecasts should distinguish indicative demand from authorised orders or contracts. See revised clause for the complete provision.

Evidence links: S1-R05, S2-R01, S2-R02, S4-R06, S6-R01.

## C03 | 6.2.2 Payment and working capital

Baseline: Payment is mentioned in activity design but a verifiable payment pathway and financing review are absent.

Revision: Before contracting, the authorised buyer should agree the invoice requirements, receipt and acceptance evidence, responsible payment office, payment interval, discrepancy-resolution route and escalation process. Delivery, acceptance, rejection, invoicing and payment dates should be recorded so delays and their causes can be assessed. See revised clause for the complete provision.

Evidence links: S2-R06, S5-R18, S6-R01.

Still open: Payment terms, financing options and the demand-to-payment handoff require authorised agreement; the Session 2 referral and Session 5 unresolved status remain open.

## C04 | 6.2.3 Supply shortfalls and procurement targets

Baseline: The 30 percent option is retained, but exception controls and target measurement require definition.

Revision: Any proposed local-supply exception should identify the affected product, quantity, reason, evidence of supply assessment, authorising body, duration and review date. Records should support aggregated reporting and review of repeated shortfalls. See revised clause for the complete provision.

Evidence links: S2-R07, S2-R08, S4-R07.

Still open: Exception procedures and the feasibility and measurement of any target require country review. Later support for transparency does not close the earlier unresolved legal and operational questions.

## C05 | 6.3.1 Accessible registration and distinct decisions

Baseline: Supplier registration and certification are listed without a complete separation of engagement, verification and procurement decisions.

Revision: Registration should provide visibility, engagement and referral without requiring every entrant already to be certified, formally established or digitally connected. Minimum fields, verification responsibilities and update arrangements should be agreed for the defined purpose. See revised clause for the complete provision.

Evidence links: S1-R06, S2-R03, S3-R09, S4-R03, S4-R04, S4-R05, S6-R09.

Still open: Ownership, mandatory fields, eligibility rules and the response to mixed views on exclusion need confirmation.

## C06 | 6.3.2 Compliance and enterprise development

Baseline: Training provisions need a market-specific compliance and affordability pathway.

Revision: Supplier support should begin with a gap assessment against the selected product and buyer requirements and include food-safety training, verification, market-appropriate certification, traceability, costing, records and production planning. Technical and financial support options should identify compliance costs, who could meet them and the conditions for assistance. See revised clause for the complete provision.

Evidence links: S1-R07, S1-R08, S2-R04, S5-R14, S6-R02.

Still open: Compliance costs, financing and incentive design remain for technical review; training does not resolve the Session 2 Mixed View by itself.

## C07 | 6.4.1 Demand and existing assets before investment

Baseline: The baseline encourages hubs and storage expansion without explicit investment gates.

Revision: Infrastructure preparation should map verified demand, supplier capacity, existing facilities, service gaps and utilisation before recommending new construction. Compare rehabilitation, coordination of existing market houses or cooperative assets, shared services and farm networks with new facilities. See revised clause for the complete provision.

Evidence links: S3-R02, S3-R03, S3-R04, S3-R05, S3-R13, S6-R03, S6-R05.

Still open: Investment thresholds, ownership, costs and campus feasibility remain referred or under further technical review; no construction is authorised.

## C08 | 6.5.1 Integrated logistics and climate resilience

Baseline: Cold-chain expansion is proposed without specifying operational interfaces, accessibility or continuity requirements.

Revision: Aggregation, preparation, packing, storage, transport, delivery and digital records should be designed as connected services. Product-specific plans should identify temperatures, handling requirements, shelf life, collection points, routes, delivery windows, capacity and responsibilities for loss or rejection. See revised clause for the complete provision.

Evidence links: S2-R05, S3-R01, S3-R06, S3-R07, S3-R10, S3-R11, S3-R12, S3-R14.

Still open: Logistics models and affordability require technical assessment; the Session 3 Mixed View is retained.

## C09 | 6.6.1 Connected functions and interoperable services

Baseline: Digital tools are listed separately without defining the complete delivery chain or limits on a regional layer.

Revision: Digital support should connect identity and consent, supplier and product information, eligibility decisions, demand matching, orders, production scheduling, inventory, logistics, delivery confirmation, payment and evidence. Retain suitable national and institutional systems and minimise duplicate collection. See revised clause for the complete provision.

Evidence links: S3-R08, S4-R01, S4-R02, S4-R16, S4-R17, S4-R22, S6-R10.

Still open: A regional service layer remains Referred; architecture and institutional responsibilities must be reviewed before technology selection.

## C10 | 6.6.2 Data governance security and redress

Baseline: The baseline refers to sensitive information but lacks operational safeguards.

Revision: An agreed data-governance plan should identify collection purposes, consent where applicable, accountable institutions, mandatory and optional fields, access permissions, storage, retention, permitted sharing, correction, export and withdrawal arrangements where applicable. Collect only necessary information and protect personal and commercially sensitive records. See revised clause for the complete provision.

Evidence links: S1-R09, S4-R04, S4-R09, S4-R11, S4-R12, S4-R13, S4-R15, S6-R10.

Still open: Data ownership, access rules and grievance responsibilities require agreement by the relevant institutions.

## C11 | 6.6.3 Responsible artificial intelligence

Baseline: No specific AI decision safeguards are stated.

Revision: If AI is proposed for forecasting, matching, planning or early warning, its purpose, input quality, limitations and responsible human decision-maker should be documented. Test for bias and exclusion, provide understandable criteria and allow affected participants to challenge consequential outcomes through human review. See revised clause for the complete provision.

Evidence links: S4-R10.

Still open: AI use cases, accountability and appeal rules require technical and institutional review.

## C12 | 7.11.1 Documented handoffs and joint work plans

Baseline: The baseline responsibility matrix needs operational handoffs, escalation and resource links.

Revision: For each agreed activity, the participating institutions should record a work plan with activities, accepted roles, outputs, costs, resources, indicators and agreed dates. At each handoff—from demand and supplier preparation to inspection, contracting, delivery, acceptance and payment—identify the information received, decision authority, evidence passed onward and escalation route for delay. See revised clause for the complete provision.

Evidence links: S5-R01, S5-R02, S5-R03, S5-R04, S5-R05, S5-R06, S5-R07, S5-R08, S5-R18, S6-R07, S6-R08.

Still open: The regional convening role, institution-specific mandates and procurement handoffs remain subject to confirmation; no acceptance is inferred.

## C13 | 7.6.1 Youth influence and institutional continuity

Baseline: Youth roles are proposed but evidence of influence and links to governance decisions need definition.

Revision: Youth should participate early in agenda setting and design, and remain involved in testing, implementation learning, monitoring and evaluation. Agreed roles may include suppliers, processors, logisticians, researchers, communicators, technologists and service operators. See revised clause for the complete provision.

Evidence links: S1-R01, S2-R10, S2-R11, S4-R14, S4-R15, S5-R09, S5-R11, S5-R12, S5-R13, S6-R11.

Still open: The CAYAB role referral and institutional-framework questions remain open to the competent governance process.

## C14 | 8.2.1 Readiness evidence before a pilot

Baseline: Readiness assessment needs a documented decision and a wider set of feasibility tests.

Revision: A readiness record should assess buyer demand and receiving capacity; supplier volumes, seasonality and compliance; procurement and trade conditions; payment and working capital; existing infrastructure and logistics; land, water, energy and climate risks; digital access and data safeguards; accessible participation; costs, maintenance and institutional responsibilities. Findings should identify what is ready, what requires remediation and what prevents proceeding. See revised clause for the complete provision.

Evidence links: S1-R05, S4-R18, S6-R04.

Still open: Detailed country readiness criteria and assessment responsibilities remain for technical review; no pilot country is confirmed.

## C15 | 8.6.1 Appraisal of the proposed readiness and investment facility

Baseline: Resource mobilisation does not address the proposed integrated facility or grant safeguards.

Revision: A proposed procurement readiness and investment facility may be appraised as one option linking shared infrastructure and services, youth and small-enterprise readiness, and buyer demand planning, receipt and payment capacity. Any design should set transparent eligibility and scoring, conflict-of-interest controls, independent review, milestone-based funding and a documented complaints route. See revised clause for the complete provision.

Evidence links: S1-R08, S6-R06.

Still open: Facility governance, funding, safeguards and national financing options require further technical review.

## C16 | 8.7.1 Pilot stages and decision gates

Baseline: Phasing is supported but entry criteria and expansion decisions are not explicit.

Revision: An agreed pilot should specify willing buyers and suppliers, products, locations, selection criteria, objectives, costs, governance, approved financing, safeguards, baseline measures and an evaluation plan. Stages are: institutional and technical consolidation; national readiness assessment; costed pilot design; controlled testing of the complete demand-to-payment chain; and evaluation with revision, expansion or closure as justified. See revised clause for the complete provision.

Evidence links: S1-R03, S1-R04, S2-R09, S3-R15, S4-R19, S4-R20, S4-R21, S5-R16, S5-R17.

Still open: Pilot criteria, country participation, funding, timeframes and evaluation commissioning require acceptance and approvals.

## C17 | 10.2.1 Outcome measures and comparable evidence

Baseline: The baseline lists measures but needs operational definitions, baselines and limits on economic claims.

Revision: Before a pilot begins, agree indicator definitions, baselines, data sources, responsible custodians, disaggregation and reporting intervals. Separate registered, verified, certified, eligible, contracted and active suppliers. See revised clause for the complete provision.

Evidence links: S1-R10, S2-R10, S2-R12, S4-R08, S5-R15, S6-R12.

Still open: Indicator definitions, baseline evidence and thresholds remain to be agreed; the earlier no-determination status and later technical-review requirement are retained.

## C18 | 10.6.1 Recommendation response and revision control

Baseline: Continuous improvement lacks a reviewable recommendation-to-clause record and response workflow.

Revision: CAYAB proposes to maintain a controlled register with a unique recommendation ID, source session and locator, original validation status, response, affected strategy clause, revision version, outstanding issue, institution approached, accepted responsibility where confirmed and feedback to participants. Inclusion in a draft is recorded as a drafting response, not implementation or formal closure. See revised clause for the complete provision.

Evidence links: S1-R02, S5-R10, S6-R13.

Still open: The youth recommendation-response workflow remains unresolved until agreed; producing this matrix does not assign response obligations.

Related edits: the COTED paper now notes the completed consultations without enlarging its two-part recognition request. Section 6.4 conditions new hubs on assessment; section 6.6 conditions platforms on governance and existing-system review; Annex I separates supplier statuses and adds outcome indicators; Annex II separates registration from eligibility; Annex IV now follows demand through payment and feedback. Annex VI records outstanding decisions and submission review requirements. The baseline’s 30 percent ambition is retained as unvalidated and indicative; it is not attributed to consultation support. Minor spelling and document-date corrections carry no substantive change.

# Session 1 recommendation mapping

Source: CAYAB Consultation Validation Series Session 1 Report for LoA Committee.docx

| Source ID and locator | Recommendation | Source status | Revised clause and drafting response | Outstanding decision or limit |
| --- | --- | --- | --- | --- |
| S1-R01 Section 7, recommendation 1 | Endorse structured youth participation as a design requirement. Ensure the revised CAYAB framework defines recurring mechanisms for national input, regional deliberation, implementation participation and accountability. | Proposed for LoA Committee consideration | 7.6.1 (C13) Drafted: Youth influence and institutional continuity. | The CAYAB role referral and institutional-framework questions remain open to the competent governance process. Youth participation is incorporated; full institutional-framework amendments remain outside this procurement revision. |
| S1-R02 Section 7, recommendation 2 | Require a recommendation-to-response process. Record each consultation recommendation, responsible institution, disposition, action and status so participants can see how evidence is used. | Proposed for LoA Committee consideration | 1.6 (C01); 10.6.1 (C18) Drafted: Consultation basis and validation status; Recommendation response and revision control. | The youth recommendation-response workflow remains unresolved until agreed; producing this matrix does not assign response obligations. |
| S1-R03 Section 7, recommendation 3 | Develop an LAFP implementation roadmap. Translate the policy into phased activities, institutional responsibilities, resourcing requirements, timelines and measurable results. | Proposed for LoA Committee consideration | 8.7.1 (C16) Drafted: Pilot stages and decision gates. | Pilot criteria, country participation, funding, timeframes and evaluation commissioning require acceptance and approvals. |
| S1-R04 Section 7, recommendation 4 | Design a pilot programme. Test institutional procurement and local-supplier participation in selected settings before regional scaling. | Proposed for LoA Committee consideration | 8.7.1 (C16) Drafted: Pilot stages and decision gates. | Pilot criteria, country participation, funding, timeframes and evaluation commissioning require acceptance and approvals. |
| S1-R05 Section 7, recommendation 5 | Assess procurement readiness. Map institutional demand, procurement rules, payment terms, food-safety requirements, certification and producer capacity. | Proposed for LoA Committee consideration | 6.2.1 (C02); 8.2.1 (C14) Drafted: Demand planning and buyer readiness; Readiness evidence before a pilot. | Detailed country readiness criteria and assessment responsibilities remain for technical review; no pilot country is confirmed. |
| S1-R06 Section 7, recommendation 6 | Develop the supplier-registry concept. Define purpose, minimum data fields, verification, update responsibilities, data protection and links to buyers and aggregation mechanisms. | Proposed for LoA Committee consideration | 6.3.1 (C05) Drafted: Accessible registration and distinct decisions. | Ownership, mandatory fields, eligibility rules and the response to mixed views on exclusion need confirmation. |
| S1-R07 Section 7, recommendation 7 | Strengthen collective market access. Support cooperatives, producer groups and aggregation hubs that can consolidate supply and improve quality, logistics and bargaining power. | Proposed for LoA Committee consideration | 6.3.2 (C06) Drafted: Compliance and enterprise development. | Compliance costs, financing and incentive design remain for technical review; training does not resolve the Session 2 Mixed View by itself. |
| S1-R08 Section 7, recommendation 8 | Create a youth-sensitive incentive review. Assess whether existing grants, finance, training and investment mechanisms enable youth entry, retention and growth. | Proposed for LoA Committee consideration | 6.3.2 (C06); 8.6.1 (C15) Drafted: Compliance and enterprise development; Appraisal of the proposed readiness and investment facility. | Compliance costs, financing and incentive design remain for technical review; training does not resolve the Session 2 Mixed View by itself. Facility governance, funding, safeguards and national financing options require further technical review. |
| S1-R09 Section 7, recommendation 9 | Adopt an inclusion standard for innovation. Ensure technology and digital services are accessible to remote, underserved and lower-capacity producers. | Proposed for LoA Committee consideration | 6.6.2 (C10) Drafted: Data governance security and redress. | Data ownership, access rules and grievance responsibilities require agreement by the relevant institutions. |
| S1-R10 Section 7, recommendation 10 | Establish a monitoring, evaluation and learning framework. Track participation quality, recommendation uptake, procurement outcomes, youth benefit, producer performance and policy impact. | Proposed for LoA Committee consideration | 10.2.1 (C17) Drafted: Outcome measures and comparable evidence. | Indicator definitions, baseline evidence and thresholds remain to be agreed; the earlier no-determination status and later technical-review requirement are retained. |

# Session 2 recommendation mapping

Source: CAYAB Session 2 Report to LoA Committee.docx

| Source ID and locator | Recommendation | Source status | Revised clause and drafting response | Outstanding decision or limit |
| --- | --- | --- | --- | --- |
| S2-R01 Section 5, register row 1 (Market information) | Communicate institutional demand early enough to inform production, investment and delivery planning. | Supported | 6.2.1 (C02) Drafted: Demand planning and buyer readiness. | Draft incorporation recorded; revised wording remains subject to review and does not establish implementation. |
| S2-R02 Section 5, register row 2 (Local procurement) | Create fair opportunity for qualified Caribbean suppliers while maintaining safety, quality, reliability, competitiveness and value for money. | Supported | 6.2.1 (C02) Drafted: Demand planning and buyer readiness. | Draft incorporation recorded; revised wording remains subject to review and does not establish implementation. |
| S2-R03 Section 5, register row 3 (Supplier registry) | Improve producer visibility without excluding suppliers who are not yet fully formalized, certified or digitally connected. | Mixed View | 6.3.1 (C05) Drafted: Accessible registration and distinct decisions. | Ownership, mandatory fields, eligibility rules and the response to mixed views on exclusion need confirmation. |
| S2-R04 Section 5, register row 4 (Certification) | Maintain appropriate standards while providing realistic, financed pathways to compliance for small and emerging suppliers. | Mixed View | 6.3.2 (C06) Drafted: Compliance and enterprise development. | Compliance costs, financing and incentive design remain for technical review; training does not resolve the Session 2 Mixed View by itself. |
| S2-R05 Section 5, register row 5 (Aggregation and infrastructure) | Address aggregation, storage, cold chain, transport, processing, digital ordering and scheduling alongside procurement. | Supported | 6.5.1 (C08) Drafted: Integrated logistics and climate resilience. | Logistics models and affordability require technical assessment; the Session 3 Mixed View is retained. |
| S2-R06 Section 5, register row 6 (Payment arrangements) | Design payment terms and working-capital support so capable small and youth-led suppliers can participate. | Referred | 6.2.2 (C03) Drafted: Payment and working capital. | Payment terms, financing options and the demand-to-payment handoff require authorised agreement; the Session 2 referral and Session 5 unresolved status remain open. |
| S2-R07 Section 5, register row 7 (Member State adaptation) | Adapt targets, products, timetables and arrangements to differing legal, production, infrastructure, market and trade conditions. | Supported | 6.2.3 (C04) Drafted: Supply shortfalls and procurement targets. | Exception procedures and the feasibility and measurement of any target require country review. Later support for transparency does not close the earlier unresolved legal and operational questions. |
| S2-R08 Section 5, register row 8 (Import exemptions) | Define transparent exceptions where local supply is insufficient without undermining LAFP objectives. | Unresolved | 6.2.3 (C04) Drafted: Supply shortfalls and procurement targets. | Exception procedures and the feasibility and measurement of any target require country review. Later support for transparency does not close the earlier unresolved legal and operational questions. |
| S2-R09 Section 5, register row 9 (Phased pilot) | Test the LAFP through a governed, costed and evaluated pilot before considering wider implementation. | Supported | 8.7.1 (C16) Drafted: Pilot stages and decision gates. | Pilot criteria, country participation, funding, timeframes and evaluation commissioning require acceptance and approvals. |
| S2-R10 Section 5, register row 10 (Youth participation) | Measure youth participation in procurement, finance, technology, enterprise development and other value-chain opportunities. | Supported | 7.6.1 (C13); 10.2.1 (C17) Drafted: Youth influence and institutional continuity; Outcome measures and comparable evidence. | The CAYAB role referral and institutional-framework questions remain open to the competent governance process. Indicator definitions, baseline evidence and thresholds remain to be agreed; the earlier no-determination status and later technical-review requirement are retained. |
| S2-R11 Section 5, register row 11 (CAYAB role) | Define a complementary role in youth mobilization, market information, supplier visibility and monitoring. | Referred | 7.6.1 (C13) Drafted: Youth influence and institutional continuity. | The CAYAB role referral and institutional-framework questions remain open to the competent governance process. |
| S2-R12 Section 5, register row 12 (Monitoring and evaluation) | Track suppliers, procurement performance, payment, barriers, youth participation and progress against targets. | No formal determination recorded | 10.2.1 (C17) Drafted: Outcome measures and comparable evidence. | Indicator definitions, baseline evidence and thresholds remain to be agreed; the earlier no-determination status and later technical-review requirement are retained. |

# Session 3 recommendation mapping

Source: CAYAB Session 3 Report LoA Committee.docx

| Source ID and locator | Recommendation | Source status | Revised clause and drafting response | Outstanding decision or limit |
| --- | --- | --- | --- | --- |
| S3-R01 Section 5, register row 1 (Integrated infrastructure) | Treat aggregation, preparation, storage, cold chain, logistics, delivery and digital coordination as interconnected LAFP functions. | Supported | 6.5.1 (C08) Drafted: Integrated logistics and climate resilience. | Logistics models and affordability require technical assessment; the Session 3 Mixed View is retained. |
| S3-R02 Section 5, register row 2 (Demand mapping) | Map institutional demand before major infrastructure decisions. | Supported | 6.4.1 (C07) Drafted: Demand and existing assets before investment. | Investment thresholds, ownership, costs and campus feasibility remain referred or under further technical review; no construction is authorised. |
| S3-R03 Section 5, register row 3 (Existing assets) | Assess opportunities to upgrade, coordinate or repurpose existing assets before new construction. | Supported | 6.4.1 (C07) Drafted: Demand and existing assets before investment. | Investment thresholds, ownership, costs and campus feasibility remain referred or under further technical review; no construction is authorised. |
| S3-R04 Section 5, register row 4 (Utilization) | Require evidence of sufficient demand and utilization before new hubs or major facilities are considered. | Supported | 6.4.1 (C07) Drafted: Demand and existing assets before investment. | Investment thresholds, ownership, costs and campus feasibility remain referred or under further technical review; no construction is authorised. |
| S3-R05 Section 5, register row 5 (Ownership and operations) | Define ownership, operation, maintenance, replacement, monitoring and cost recovery. | Referred | 6.4.1 (C07) Drafted: Demand and existing assets before investment. | Investment thresholds, ownership, costs and campus feasibility remain referred or under further technical review; no construction is authorised. |
| S3-R06 Section 5, register row 6 (Climate resilience) | Integrate climate risk, water management, irrigation and resilient design into planning and finance. | Supported | 6.5.1 (C08) Drafted: Integrated logistics and climate resilience. | Logistics models and affordability require technical assessment; the Session 3 Mixed View is retained. |
| S3-R07 Section 5, register row 7 (Logistics and transport) | Coordinate product-specific storage, routes, collection points, delivery windows and service providers. | Mixed View | 6.5.1 (C08) Drafted: Integrated logistics and climate resilience. | Logistics models and affordability require technical assessment; the Session 3 Mixed View is retained. |
| S3-R08 Section 5, register row 8 (Digital coordination) | Connect buyers, suppliers, inventory, orders, transport, delivery, payment and accountability information. | Supported | 6.6.1 (C09) Drafted: Connected functions and interoperable services. | A regional service layer remains Referred; architecture and institutional responsibilities must be reviewed before technology selection. |
| S3-R09 Section 5, register row 9 (Supplier visibility) | Use a living supplier registry or comparable mechanism without treating it as automatic certification. | Referred | 6.3.1 (C05) Drafted: Accessible registration and distinct decisions. | Ownership, mandatory fields, eligibility rules and the response to mixed views on exclusion need confirmation. |
| S3-R10 Section 5, register row 10 (Youth-led services) | Enable qualified youth enterprises to participate across infrastructure and market services. | Supported | 6.5.1 (C08) Drafted: Integrated logistics and climate resilience. | Logistics models and affordability require technical assessment; the Session 3 Mixed View is retained. |
| S3-R11 Section 5, register row 11 (Accessibility) | Apply universal-design and accessibility requirements across facilities, transport and digital systems. | Supported | 6.5.1 (C08) Drafted: Integrated logistics and climate resilience. | Logistics models and affordability require technical assessment; the Session 3 Mixed View is retained. |
| S3-R12 Section 5, register row 12 (Community participation) | Engage intended users and affected communities before decisions become irreversible. | Supported | 6.5.1 (C08) Drafted: Integrated logistics and climate resilience. | Logistics models and affordability require technical assessment; the Session 3 Mixed View is retained. |
| S3-R13 Section 5, register row 13 (Investment readiness) | Establish evidence standards for demand, project preparation, climate risk, environmental requirements and viability. | Referred | 6.4.1 (C07) Drafted: Demand and existing assets before investment. | Investment thresholds, ownership, costs and campus feasibility remain referred or under further technical review; no construction is authorised. |
| S3-R14 Section 5, register row 14 (Private-sector and tourism linkages) | Strengthen farm-to-hotel, processing, distribution and other commercial market connections. | Supported | 6.5.1 (C08) Drafted: Integrated logistics and climate resilience. | Logistics models and affordability require technical assessment; the Session 3 Mixed View is retained. |
| S3-R15 Section 5, register row 15 (Bounded pilot) | Test the relevant LAFP functions through a governed, costed and evaluated national pilot. | Supported | 8.7.1 (C16) Drafted: Pilot stages and decision gates. | Pilot criteria, country participation, funding, timeframes and evaluation commissioning require acceptance and approvals. |

# Session 4 recommendation mapping

Source: CAYAB Session 4 Report LoA Committee.docx

| Source ID and locator | Recommendation | Source status | Revised clause and drafting response | Outstanding decision or limit |
| --- | --- | --- | --- | --- |
| S4-R01 Section 5, register No. 1 | Connect identity and consent, eligibility, supplier information, matching, orders, delivery, payment and evidence. | Supported | 6.6.1 (C09) Drafted: Connected functions and interoperable services. | A regional service layer remains Referred; architecture and institutional responsibilities must be reviewed before technology selection. |
| S4-R02 Section 5, register No. 2 | Connect national and institutional systems through common rules and minimum approved information. | Supported | 6.6.1 (C09) Drafted: Connected functions and interoperable services. | A regional service layer remains Referred; architecture and institutional responsibilities must be reviewed before technology selection. |
| S4-R03 Section 5, register No. 3 | Develop the Living Registry as a governed entry and engagement layer with profiles, skills, interests and consent. | Supported | 6.3.1 (C05) Drafted: Accessible registration and distinct decisions. | Ownership, mandatory fields, eligibility rules and the response to mixed views on exclusion need confirmation. |
| S4-R04 Section 5, register No. 4 | Provide assisted registration, mobile-friendly access and offline or alternative pathways. | Supported | 6.3.1 (C05); 6.6.2 (C10) Drafted: Accessible registration and distinct decisions; Data governance security and redress. | Ownership, mandatory fields, eligibility rules and the response to mixed views on exclusion need confirmation. Data ownership, access rules and grievance responsibilities require agreement by the relevant institutions. |
| S4-R05 Section 5, register No. 5 | Separate registration from certification, procurement approval and supplier eligibility decisions. | Supported | 6.3.1 (C05) Drafted: Accessible registration and distinct decisions. | Ownership, mandatory fields, eligibility rules and the response to mixed views on exclusion need confirmation. |
| S4-R06 Section 5, register No. 6 | Communicate expected quantities, standards, locations and delivery dates early enough for supplier planning. | Supported | 6.2.1 (C02) Drafted: Demand planning and buyer readiness. | Draft incorporation recorded; revised wording remains subject to review and does not establish implementation. |
| S4-R07 Section 5, register No. 7 | Make any local-supply exception transparent, time-bound, product-specific and supported by recorded reasons. | Supported | 6.2.3 (C04) Drafted: Supply shortfalls and procurement targets. | Exception procedures and the feasibility and measurement of any target require country review. Later support for transparency does not close the earlier unresolved legal and operational questions. |
| S4-R08 Section 5, register No. 8 | Measure implementation outcomes rather than registration activity alone. | Supported | 10.2.1 (C17) Drafted: Outcome measures and comparable evidence. | Indicator definitions, baseline evidence and thresholds remain to be agreed; the earlier no-determination status and later technical-review requirement are retained. |
| S4-R09 Section 5, register No. 9 | Use aggregated public reporting and protect personal and commercially sensitive information. | Supported | 6.6.2 (C10) Drafted: Data governance security and redress. | Data ownership, access rules and grievance responsibilities require agreement by the relevant institutions. |
| S4-R10 Section 5, register No. 10 | Use AI responsibly with understandable criteria, human review, bias testing and challenge mechanisms. | Supported | 6.6.3 (C11) Drafted: Responsible artificial intelligence. | AI use cases, accountability and appeal rules require technical and institutional review. |
| S4-R11 Section 5, register No. 11 | Define consent, data responsibility, permitted use, access, storage, sharing, correction, export and withdrawal rules. | Supported | 6.6.2 (C10) Drafted: Data governance security and redress. | Data ownership, access rules and grievance responsibilities require agreement by the relevant institutions. |
| S4-R12 Section 5, register No. 12 | Build in role-based access, encryption, access logs, tested backups and incident response. | Supported | 6.6.2 (C10) Drafted: Data governance security and redress. | Data ownership, access rules and grievance responsibilities require agreement by the relevant institutions. |
| S4-R13 Section 5, register No. 13 | Provide visible grievance and appeal mechanisms for decisions affecting opportunities. | Supported | 6.6.2 (C10) Drafted: Data governance security and redress. | Data ownership, access rules and grievance responsibilities require agreement by the relevant institutions. |
| S4-R14 Section 5, register No. 14 | Include youth in design, governance, testing and evaluation. | Supported | 7.6.1 (C13) Drafted: Youth influence and institutional continuity. | The CAYAB role referral and institutional-framework questions remain open to the competent governance process. |
| S4-R15 Section 5, register No. 15 | Account for differences in location, digital literacy, disability, gender and connectivity. | Supported | 6.6.2 (C10); 7.6.1 (C13) Drafted: Data governance security and redress; Youth influence and institutional continuity. | Data ownership, access rules and grievance responsibilities require agreement by the relevant institutions. The CAYAB role referral and institutional-framework questions remain open to the competent governance process. |
| S4-R16 Section 5, register No. 16 | Connect with existing agricultural systems and institutions to reduce duplication. | Supported | 6.6.1 (C09) Drafted: Connected functions and interoperable services. | A regional service layer remains Referred; architecture and institutional responsibilities must be reviewed before technology selection. |
| S4-R17 Section 5, register No. 17 | Further explore an interoperable regional service layer connecting approved services. | Referred | 6.6.1 (C09) Drafted: Connected functions and interoperable services. | A regional service layer remains Referred; architecture and institutional responsibilities must be reviewed before technology selection. |
| S4-R18 Section 5, register No. 18 | Assess demand, suppliers, infrastructure, service gaps, legal conditions and responsibilities before piloting. | Supported | 8.2.1 (C14) Drafted: Readiness evidence before a pilot. | Detailed country readiness criteria and assessment responsibilities remain for technical review; no pilot country is confirmed. |
| S4-R19 Section 5, register No. 19 | Establish governance, security, financing, safeguards and evaluation arrangements before a pilot. | Supported | 8.7.1 (C16) Drafted: Pilot stages and decision gates. | Pilot criteria, country participation, funding, timeframes and evaluation commissioning require acceptance and approvals. |
| S4-R20 Section 5, register No. 20 | Define pilot selection criteria, objectives, risks, limitations and success measures. | Supported | 8.7.1 (C16) Drafted: Pilot stages and decision gates. | Pilot criteria, country participation, funding, timeframes and evaluation commissioning require acceptance and approvals. |
| S4-R21 Section 5, register No. 21 | Consider independent evaluation before wider regional application. | Supported | 8.7.1 (C16) Drafted: Pilot stages and decision gates. | Pilot criteria, country participation, funding, timeframes and evaluation commissioning require acceptance and approvals. |
| S4-R22 Section 5, register No. 22 | Agree public purpose, accessibility, data rules, service standards, ownership, governance, financing and exit arrangements before technology selection. | Supported | 6.6.1 (C09) Drafted: Connected functions and interoperable services. | A regional service layer remains Referred; architecture and institutional responsibilities must be reviewed before technology selection. |

# Session 5 recommendation mapping

Source: CAYAB Session 5 Report LoA Committee.docx

| Source ID and locator | Recommendation | Source status | Revised clause and drafting response | Outstanding decision or limit |
| --- | --- | --- | --- | --- |
| S5-R01 Section 4, register No. 1 | Nationally led implementation with defined regional support. | Supported | 7.11.1 (C12) Drafted: Documented handoffs and joint work plans. | The regional convening role, institution-specific mandates and procurement handoffs remain subject to confirmation; no acceptance is inferred. |
| S5-R02 Section 4, register No. 2 | Formal implementation and accountability framework. | Supported | 7.11.1 (C12) Drafted: Documented handoffs and joint work plans. | The regional convening role, institution-specific mandates and procurement handoffs remain subject to confirmation; no acceptance is inferred. |
| S5-R03 Section 4, register No. 3 | Use suitable existing institutions, mandates and reporting systems. | Supported | 7.11.1 (C12) Drafted: Documented handoffs and joint work plans. | The regional convening role, institution-specific mandates and procurement handoffs remain subject to confirmation; no acceptance is inferred. |
| S5-R04 Section 4, register No. 4 | Readiness assessments, focal points and documented handoffs. | Supported | 7.11.1 (C12) Drafted: Documented handoffs and joint work plans. | The regional convening role, institution-specific mandates and procurement handoffs remain subject to confirmation; no acceptance is inferred. |
| S5-R05 Section 4, register No. 5 | Explicit handoffs across direction, coordination, delivery, technical support and accountability. | Supported | 7.11.1 (C12) Drafted: Documented handoffs and joint work plans. | The regional convening role, institution-specific mandates and procurement handoffs remain subject to confirmation; no acceptance is inferred. |
| S5-R06 Section 4, register No. 6 | Joint work plan with activities, responsibilities, resources, timelines and indicators. | Supported | 7.11.1 (C12) Drafted: Documented handoffs and joint work plans. | The regional convening role, institution-specific mandates and procurement handoffs remain subject to confirmation; no acceptance is inferred. |
| S5-R07 Section 4, register No. 7 | Decision and escalation arrangements for delivery delays. | Supported | 7.11.1 (C12) Drafted: Documented handoffs and joint work plans. | The regional convening role, institution-specific mandates and procurement handoffs remain subject to confirmation; no acceptance is inferred. |
| S5-R08 Section 4, register No. 8 | Partner roles within approved mandates and agreed work programmes. | Supported | 7.11.1 (C12) Drafted: Documented handoffs and joint work plans. | The regional convening role, institution-specific mandates and procurement handoffs remain subject to confirmation; no acceptance is inferred. |
| S5-R09 Section 4, register No. 9 | Documented youth roles across consultation, delivery, learning, monitoring and feedback. | Supported | 7.6.1 (C13) Drafted: Youth influence and institutional continuity. | The CAYAB role referral and institutional-framework questions remain open to the competent governance process. |
| S5-R10 Section 4, register No. 10 | Mechanism to track, answer and report youth recommendations. | Unresolved | 10.6.1 (C18) Drafted: Recommendation response and revision control. | The youth recommendation-response workflow remains unresolved until agreed; producing this matrix does not assign response obligations. |
| S5-R11 Section 4, register No. 11 | Early youth participation in policy and programme decisions. | Supported | 7.6.1 (C13) Drafted: Youth influence and institutional continuity. | The CAYAB role referral and institutional-framework questions remain open to the competent governance process. |
| S5-R12 Section 4, register No. 12 | Fair access to practical youth roles with consent and safeguarding. | Supported | 7.6.1 (C13) Drafted: Youth influence and institutional continuity. | The CAYAB role referral and institutional-framework questions remain open to the competent governance process. |
| S5-R13 Section 4, register No. 13 | Include women, rural and underserved youth and those outside formal networks. | Supported | 7.6.1 (C13) Drafted: Youth influence and institutional continuity. | The CAYAB role referral and institutional-framework questions remain open to the competent governance process. |
| S5-R14 Section 4, register No. 14 | Support agricultural registration, validation and record keeping. | Supported | 6.3.2 (C06) Drafted: Compliance and enterprise development. | Compliance costs, financing and incentive design remain for technical review; training does not resolve the Session 2 Mixed View by itself. |
| S5-R15 Section 4, register No. 15 | Measure outcomes beyond activities. | Supported | 10.2.1 (C17) Drafted: Outcome measures and comparable evidence. | Indicator definitions, baseline evidence and thresholds remain to be agreed; the earlier no-determination status and later technical-review requirement are retained. |
| S5-R16 Section 4, register No. 16 | Phased preparation, piloting, review and possible expansion. | Supported | 8.7.1 (C16) Drafted: Pilot stages and decision gates. | Pilot criteria, country participation, funding, timeframes and evaluation commissioning require acceptance and approvals. |
| S5-R17 Section 4, register No. 17 | Identify willing pilot countries following appropriate approval. | Referred | 8.7.1 (C16) Drafted: Pilot stages and decision gates. | Pilot criteria, country participation, funding, timeframes and evaluation commissioning require acceptance and approvals. |
| S5-R18 Section 4, register No. 18 | Connect demand forecasting, supplier preparation, contracting and payment. | Unresolved | 6.2.2 (C03); 7.11.1 (C12) Drafted: Payment and working capital; Documented handoffs and joint work plans. | Payment terms, financing options and the demand-to-payment handoff require authorised agreement; the Session 2 referral and Session 5 unresolved status remain open. The regional convening role, institution-specific mandates and procurement handoffs remain subject to confirmation; no acceptance is inferred. |

# Session 6 recommendation mapping

Source: CAYAB Session 6 Report to LoA Committee.docx

| Source ID and locator | Recommendation | Source status | Revised clause and drafting response | Outstanding decision or limit |
| --- | --- | --- | --- | --- |
| S6-R01 Section 5, register No. 1 | Use institutional demand and payment arrangements to inform production planning. | Supported in discussion | 6.2.1 (C02); 6.2.2 (C03) Drafted: Demand planning and buyer readiness; Payment and working capital. | Payment terms, financing options and the demand-to-payment handoff require authorised agreement; the Session 2 referral and Session 5 unresolved status remain open. |
| S6-R02 Section 5, register No. 2 | Provide food-safety training, verification and market-appropriate certification in supplier development. | Supported in discussion | 6.3.2 (C06) Drafted: Compliance and enterprise development. | Compliance costs, financing and incentive design remain for technical review; training does not resolve the Session 2 Mixed View by itself. |
| S6-R03 Section 5, register No. 3 | Assess existing assets, utilisation and operating requirements before infrastructure investment. | Further technical review | 6.4.1 (C07) Drafted: Demand and existing assets before investment. | Investment thresholds, ownership, costs and campus feasibility remain referred or under further technical review; no construction is authorised. |
| S6-R04 Section 5, register No. 4 | Undertake country readiness assessment before major pilot investment. | Further technical review | 8.2.1 (C14) Drafted: Readiness evidence before a pilot. | Detailed country readiness criteria and assessment responsibilities remain for technical review; no pilot country is confirmed. |
| S6-R05 Section 5, register No. 5 | Assess the youth incubation campus against country needs rather than impose a fixed model. | Further technical review | 6.4.1 (C07) Drafted: Demand and existing assets before investment. | Investment thresholds, ownership, costs and campus feasibility remain referred or under further technical review; no construction is authorised. |
| S6-R06 Section 5, register No. 6 | Further design and appraise the integrated procurement readiness and investment facility and its safeguards. | Further technical review | 8.6.1 (C15) Drafted: Appraisal of the proposed readiness and investment facility. | Facility governance, funding, safeguards and national financing options require further technical review. |
| S6-R07 Section 5, register No. 7 | Clearly assign national responsibility for supplier readiness, certification, payment, data and complaints. | Supported in discussion | 7.11.1 (C12) Drafted: Documented handoffs and joint work plans. | The regional convening role, institution-specific mandates and procurement handoffs remain subject to confirmation; no acceptance is inferred. |
| S6-R08 Section 5, register No. 8 | Keep regional technical contributions subject to institutional mandates and formal arrangements. | Referred | 7.11.1 (C12) Drafted: Documented handoffs and joint work plans. | The regional convening role, institution-specific mandates and procurement handoffs remain subject to confirmation; no acceptance is inferred. |
| S6-R09 Section 5, register No. 9 | Distinguish Living Registry participation from certification, procurement eligibility and funding. | Supported in discussion | 6.3.1 (C05) Drafted: Accessible registration and distinct decisions. | Ownership, mandatory fields, eligibility rules and the response to mixed views on exclusion need confirmation. |
| S6-R10 Section 5, register No. 10 | Support national digital systems with low-bandwidth access, correction and review mechanisms. | Supported in discussion | 6.6.1 (C09); 6.6.2 (C10) Drafted: Connected functions and interoperable services; Data governance security and redress. | A regional service layer remains Referred; architecture and institutional responsibilities must be reviewed before technology selection. Data ownership, access rules and grievance responsibilities require agreement by the relevant institutions. |
| S6-R11 Section 5, register No. 11 | Include youth in the design and evaluation of implementation arrangements. | Supported in discussion | 7.6.1 (C13) Drafted: Youth influence and institutional continuity. | The CAYAB role referral and institutional-framework questions remain open to the competent governance process. |
| S6-R12 Section 5, register No. 12 | Agree pilot indicators and a baseline before implementation. | Further technical review | 10.2.1 (C17) Drafted: Outcome measures and comparable evidence. | Indicator definitions, baseline evidence and thresholds remain to be agreed; the earlier no-determination status and later technical-review requirement are retained. |
| S6-R13 Section 5, register No. 13 | Maintain a traceable recommendation register through subsequent revisions. | Supported in discussion | 1.6 (C01); 10.6.1 (C18) Drafted: Consultation basis and validation status; Recommendation response and revision control. | The youth recommendation-response workflow remains unresolved until agreed; producing this matrix does not assign response obligations. |

# Source register and review route

BASELINE — CAYAB Recognition and Procurement Strategy.docx

S1 — CAYAB Consultation Validation Series Session 1 Report for LoA Committee.docx

S2 — CAYAB Session 2 Report to LoA Committee.docx

S3 — CAYAB Session 3 Report LoA Committee.docx

S4 — CAYAB Session 4 Report LoA Committee.docx

S5 — CAYAB Session 5 Report LoA Committee.docx

S6 — CAYAB Session 6 Report to LoA Committee.docx

FINAL — CAYAB_Final_Consultation_and_Validation_Series_Report_LoA_Committee.docx

Source hierarchy: the latest user-supplied strategy controls the baseline; the six Committee reports control recommendation wording and source status; the final report supports cross-session synthesis. Source status has not been replaced by the broader wording of the synthesis. The original strategy and reports remain unchanged.

Proposed route: LoA review of the record and drafting responses; technical and institutional consideration of open matters; confirmation of source corrections and any additional validation evidence; finalisation of the COTED submission through the authorised process. Record the reviewer, institution, date, version, affected recommendation IDs, decision, reasons and evidence reference. No review, institutional acceptance or COTED decision is pre-filled.